## Team1_Estimated_Effort
Note: Beyond Iteration 2, nothing is changed.
Task Name: (Dependencies top to bottom) | [8 empty] | Samuel | Alivia | Zach | Yazdan | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 10 |  | 0
|  | Design architecture | Project Manager | Samuel Lim | 10 |  | 0 |  | - | - |  |  | 0
| Requirements |  |  |  |  | 7 |  | 0 |  |  |  |  | 0
|  | Gather | Requirements Engineer | Zachary Zoltek, Samuel Lim | 1 |  | 0 |  | - | - |  |  | 0
|  | Analyze | Requirements Engineer | Zachary Zoltek, Samuel Lim | 2 |  | 0 |  | - | - |  |  | 0
|  | Specify | Requirements Engineer | Zachary Zoltek, Samuel Lim | 4 |  | 0 |  | - | - |  |  | 0
| Documentation |  |  |  |  | 29 |  | 0 |  |  |  |  | 0
|  | Project Charter | Project Manager | Samuel Lim | 1 |  | 0 |  | - | - |  |  | 0
|  | Release Plan | Project Manager | Samuel Lim | 2 |  | 0 |  | - | - |  |  | 0
|  | Requirements Document | Project Manager, Requirements Engineer | Samuel Lim, Zach Zoltek | 7 |  | 0 |  | - | - |  |  | 0
|  | Project Plan | Project Manager, Developers | Samuel Lim, Alivia Dutcher, Zach Zoltek | 5 |  | 0 |  | - | - |  | - | 0
|  | Architecture Document | Architect | Yazdan Riazi, Samuel Lim | 4 |  | 0 |  | - | - |  |  | 0
|  | Test Report | Tester | Zach Zoltek, Samuel Lim | 8 |  | 0 |  | - | - |  |  | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Alivia Dutcher, Yazdan Riazi, Zach Zoltek, Samuel Lim | 2 |  | 0 |  | - | - |  | - | 0
Coding | [6 empty] | 0 | [5 empty] | 0
Iteration 1: | Development |  |  |  |  | 47 |  | 3.6 |  |  |  |  | 0
|  | Determine technology needs | Developer | Alivia Dutcher, Yazdan Riazi, Zach Zoltek, Samuel Lim | 2 |  | 1.1 |  | 0.3 | 0.3 | 0.3 | 0.2 | 1.1
|  | Research and learn new language and environment | Developer | Alivia Dutcher, Zach Zoltek, Samuel Lim | 15 |  | 2.5 |  | 2.5 |  | - | - | 2.5
|  | Set up double proxy for HTTP server | Developer | Alivia Dutcher | 2 |  | 0 |  | - |  |  |  | 0
|  | Set up autodoc tooling for CI pipelines | Developer | Zach Zoltek | 1 |  | 0 |  | - |  |  |  | 0
|  | Implement foundational HTTP logic | Developer | Alivia Dutcher | 12 |  | 0 |  |  |  |  | - | 0
|  | Create HTTP handling code (client) | Developer | Alivia Dutcher | 4 |  | 0 |  |  |  |  | - | 0
|  | Write user token handling locally | Developer | Yazdan Riazai | 1 |  | 0 |  |  |  |  | - | 0
|  | Write code for managing HTTP session | Developer | Zach Zoltek | 6 |  | 0 |  |  |  |  | - | 0
|  | Unit Testing | Developer | Zach Zoltek, Yazdan Riazi | 4 |  | 0 |  |  |  |  | - | 0
| Analysis |  |  |  |  | 10 |  | 0 |  |  |  |  | 0
|  | System and Environment Testing | Tester | Zach Zoltek | 2 |  | 0 |  | - | - |  |  | 0
|  | Bug fixes as required | Tester, Developer | Alivia Dutcher, Zach Zoltek | 3 |  | 0 |  |  |  |  | - | 0
|  | Evaluate needs for next iteration | Project Manager | Samuel Lim | 5 |  | 0 |  | - | - |  |  | 0
Iteration 2: | Design |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Implement any design changes | Project Manager |  | - |  | 0 |  | - |  |  |  | 0
|  | Risk analysis | Project Manager |  | - |  | 0 |  | - | - |  |  | 0
|  | Design XML format | Developer |  | - |  | 0 |  |  |  |  | - | 0
|  | Design Perl XML-handling code | Developer |  | - |  | 0 | [5 empty] | 0
|  | Create UI design for balance screen | Developer |  | - |  | 0 |  |  |  |  | - | 0
| Development |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Review requirements | Developer |  | - |  | 0 |  |  |  | - | - | 0
|  | Create XML parsing code | Developer |  | - |  | 0 |  |  |  | - |  | 0
|  | Handle XML data structure for retrieving balance | Developer |  | - |  | 0 |  | - |  | - |  | 0
|  | Implement UI | Developer |  | - |  | 0 |  |  |  | - | - | 0
|  | Unit Testing | Developer |  | - |  | 0 |  |  |  | - |  | 0
| Analysis |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | System Testing | Tester |  | - |  | 0 |  | - | - |  |  | 0
|  | Bug fix as required | Tester, Developer |  | - |  | 0 |  | - |  | - | - | 0
|  | Evaluate needs for next iteration | Project Manager |  | - |  | 0 |  | - |  |  |  | 0
Iteration 3: | Design |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Implement any design changes | Project Manager |  | - |  | 0 |  | - |  |  |  | 0
|  | Risk analysis | Project Manager |  | - |  | 0 |  | - | - |  |  | 0
|  | Create UI design for vendor locations | Developer |  | - |  | 0 |  | - |  |  | - | 0
|  | Design data structure for RSS location list | Developer |  | - |  | 0 |  | - |  |  |  | 0
| Development |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Review requirements | Developer |  | - |  | 0 | [5 empty] | 0
|  | Develop code for processing vendor locations | Developer |  | - |  | 0 |  |  |  |  | - | 0
|  | Implement vendor map display | Developer |  | - |  | 0 |  |  |  |  | - | 0
|  | Display vendor information | Developer |  | - |  | 0 |  |  |  |  | - | 0
|  | Unit Testing | Developer |  | - |  | 0 | [5 empty] | 0
| Analysis |  |  |  |  | 0 |  | 0 |  |  |  |  | 0
|  | Acceptance Testing | Tester, Project Manager |  | - |  | 0 |  | - | - |  |  | 0
|  | Bug fix as required | Tester, Developer |  | - |  | 0 |  | - |  |  | - | 0
Total |  |  |  |  | 103 | 103 | 3.6 | 3.6 | 2.8 | 0.3 | 0.3 | 0.2 | 3.6