## Team1_Estimated_Effort
Note: Beyond Iteration 2, nothing is changed.
Task Name: (Dependencies top to bottom) | [9 empty] | Samuel | Alivia | Zach | Yazdan | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | Status | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 10 |  | 9
|  | Design architecture | Project Manager | Samuel Lim | 10 |  | 9 |  |  | 4 | 2 | 2 | 1 | 9
| Requirements |  |  |  |  | 7 |  | 1.2 | [5 empty] | 0
|  | Gather | Requirements Engineer | Zachary Zoltek, Samuel Lim | 1 |  | 1.2 |  |  | 0.3 | 0.2 | 0.5 | 0.2 | 1.2
|  | Analyze | Requirements Engineer | Zachary Zoltek, Samuel Lim | 2 |  | 0 | [6 empty] | 0
|  | Specify | Requirements Engineer | Zachary Zoltek, Samuel Lim | 4 |  | 0 | [6 empty] | 0
| Documentation |  |  |  |  | 29 |  | 16.5 | [5 empty] | 0
|  | Project Charter | Project Manager | Samuel Lim | 1 |  | 4 |  |  | 1 | 1 | 1 | 1 | 4
|  | Release Plan | Project Manager | Samuel Lim | 2 |  | 0.7 |  |  | 0.3 | 0.4 |  |  | 0.7
|  | Requirements Document | Project Manager, Requirements Engineer | Samuel Lim, Zach Zoltek | 7 |  | 6.3 |  |  | 2 | 2 | 2 | 0.3 | 6.3
|  | Project Plan | Project Manager, Developers | Samuel Lim, Alivia Dutcher, Zach Zoltek | 5 |  | 5.5 |  |  | 1.5 | 1.5 | 1.5 | 1 | 5.5
|  | Architecture Document | Architect | Yazdan Riazi, Samuel Lim | 4 |  | 0 | [6 empty] | 0
|  | Test Report | Tester | Zach Zoltek, Samuel Lim | 8 |  | 0 | [6 empty] | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Alivia Dutcher, Yazdan Riazi, Zach Zoltek, Samuel Lim | 2 |  | 0 | [6 empty] | 0
Coding | [6 empty] | 0 | [6 empty] | 0
Iteration 1: | Development |  |  |  |  | 47 |  | 17 | [5 empty] | 0
|  | Determine technology needs | Developer | Alivia Dutcher, Yazdan Riazi, Zach Zoltek, Samuel Lim | 2 |  | 1.7 |  | IP | 0.6 | 0.4 | 0.5 | 0.2 | 1.7
|  | Research and learn new language and environment | Developer | Alivia Dutcher, Zach Zoltek, Samuel Lim | 15 |  | 13 |  | Done | 4 | 3 | 3.5 | 2.5 | 13
|  | Set up double proxy for HTTP server | Developer | Alivia Dutcher | 2 |  | 0.8 |  | Done | 0.5 |  | 0.3 |  | 0.8
|  | Set up autodoc tooling for CI pipelines | Developer | Zach Zoltek | 1 |  | 0.6 |  | Done | 0.3 | 0 | 0.3 | 0 | 0.6
|  | Implement foundational HTTP logic | Developer | Alivia Dutcher | 12 |  | 0.3 |  | IP | 0.3 |  |  |  | 0.3
|  | Create HTTP handling code (client) | Developer | Alivia Dutcher | 4 |  | 0.3 |  | IP | 0.3 |  |  |  | 0.3
|  | Write user token handling locally | Developer | Yazdan Riazi | 1 |  | 0 |  | Todo |  |  |  |  | 0
|  | Write code for managing HTTP session | Developer | Zach Zoltek | 6 |  | 0 |  | Todo |  |  |  |  | 0
|  | Unit Testing | Developer | Zach Zoltek, Yazdan Riazi | 4 |  | 0.3 |  | IP |  |  | 0.3 |  | 0.3
| Analysis |  |  |  |  | 10 |  | 5.2 | [5 empty] | 0
|  | System and Environment Testing | Tester | Zach Zoltek | 2 |  | 1.7 |  | Done | 0.5 | 0.5 | 0.5 | 0.2 | 1.7
|  | Bug fixes as required | Tester, Developer | Alivia Dutcher, Zach Zoltek | 3 |  | 0 |  | N/A | 0 | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | Samuel Lim | 5 |  | 3.5 |  | Done | 2 | 0.5 | 0.5 | 0.5 | 3.5
Iteration 2: | Design |  |  |  |  | 15.5 |  | 7 | [5 empty] | 0
|  | Implement any design changes | Project Manager | Samuel Lim | 3 |  | 1.5 |  | IR | 0.5 | 0.5 | 0.5 | - | 1.5
|  | Risk analysis | Project Manager | Samuel Lim | 4 |  | 3.5 |  | Done | 1 | 1 | 1 | 0.5 | 3.5
|  | Design container format (schedule) | Developer | Alivia Dutcher, Samuel Lim | 2.5 |  | 0 |  | Todo | - | - | - | - | 0
|  | Design drop-in format parsing | Developer | Alivia Dutcher, Samuel Lim | 4 |  | 0 |  | Todo | - | - | - | - | 0
|  | Create UI design for main page | Developer | Zach Zoltek | 2 |  | 2 |  | IP | 0.5 | 0.75 | 0.75 | - | 2
| Development |  |  |  |  | 11 |  | 6.4 | [5 empty] | 0
|  | Review requirements | Developer | Alivia Dutcher, Zach Zoltek, Samuel Lim | 4 |  | 4.6 |  | Done | 1.2 | 1.2 | 1.2 | 1 | 4.6
|  | Connect client and session HTTP logic | Developer | Alivia Dutcher, Zach Zoltek | 2.5 |  | 0.8 |  | IR | 0.8 | - | - | - | 0.8
|  | Handle basic token generation | Developer | Yazdan Riazi | 1 |  | 0 |  | Todo | - | - | - | - | 0
|  | Implement design structure for main page | Developer | Zach Zoltek | 2 |  | 0 |  | Todo | - | - | - | - | 0
|  | Unit Testing | Developer | Zach Zoltek, Yazdan Riazi | 1.5 |  | 1 |  | IP | 0.5 | - | 0.5 | - | 1
| Analysis |  |  |  |  | 7 |  | 4.7 | [5 empty] | 0
|  | System and Environment Testing | Tester | Zach Zoltek | 2 |  | 1.5 |  | IR | 0.5 | - | 1 | - | 1.5
|  | Bug fix as required | Tester, Developer | Alivia Dutcher, Zach Zoltek | 2 |  | 0 |  | N/A | 0 | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | Samuel Lim | 3 |  | 3.2 |  | Done | 1.2 | 1.2 | 0.5 | 0.3 | 3.2
Iteration 3: | Design |  |  |  |  | 13 |  | 1 | [5 empty] | 0
|  | Implement any design changes | Project Manager | Samuel Lim | 2 |  | 0.1 |  | IP | 0.1 |  |  |  | 0.1
|  | Risk analysis | Project Manager | Samuel Lim, Alivia Dutcher | 4 |  | 0.9 |  | IP | 0.3 | 0.3 | 0.3 |  | 0.9
|  | Create UI design for main page | Developer | Zach Zoltek | 4 |  | 0 |  | IP | - | - | - | - | 0 | *Snowplow from Iteration #2
|  | Design data structure for schedule constraints | Developer | Alivia Dutcher | 3 |  | 0 |  | Todo |  |  |  |  | 0 | *Snowplow from Iteration #2
| Development |  |  |  |  | 18.5 |  | 0 | [5 empty] | 0
|  | Review requirements | Developer | Alivia Dutcher | 4 |  | 0 |  | Todo |  |  |  |  | 0
|  | Develop code for processing scheduling data | Developer | Alivia Dutcher, Samuel Lim | 3 |  | 0 |  | Todo |  |  |  |  | 0
|  | Implement client-API integration | Developer | Yazdan Riazi | 6 |  | 0 |  | Todo |  |  |  |  | 0
|  | Display scheduling information | Developer | Alivia Dutcher | 4 |  | 0 |  | Todo |  |  |  |  | 0
|  | Unit Testing | Developer | Zach Zoltek | 1.5 |  | 0 |  | Todo |  |  |  |  | 0
| Analysis |  |  |  |  | 4 |  | 0 | [5 empty] | 0
|  | Acceptance Testing | Tester, Project Manager | Zach Zoltek, Samuel Lim | 2 |  | 0 |  | Todo |  |  |  |  | 0
|  | Bug fix as required | Tester, Developer | Alivia Dutcher, Zach Zoltek | 2 |  | 0 |  | Todo |  |  |  |  | 0
Total |  |  |  |  | 172 | 172 | 68 | 68 |  | 24.2 | 16.45 | 18.65 | 8.7 | 68